## Table of Contents
TABLE OF CONTENTS
Plan Review and Revision >>>
Local Health Department
Continuity of Operations Planning Workbook
I. Introduction
| Reference Sheet Name | Description
| Review and Update | Provides an on-going record of the department’s review and editing of this COOP plan, beginning with its first issue. The department’s COOP Plan should be reviewed and revised whenever there is a staffing change within the department, and at least twice a year.
II. COOP Worksheets
| Reference Sheet Name | Description
| Health Department Information | Identifies department functions and department COOP contacts.
| Leadership Succession | Identifies the order of succession to key positions within the organization. Orders should be of sufficient depth to ensure the organization’s ability to manage and direct its essential functions and operations.
| Delegation of Authority | Delegations of Authority specify who is authorized to make decisions or act on behalf of key institution or division personnel. Certain incumbents in positions specified in the orders of succession are delegated authority to perform all duties and responsibilities of the leader. Authority to act as a successor should be exercised only with reasonable certainty that a superior is unable and unavailable to exercise authority and when immediate action is required. An individual acting as successor should be relieved of his or her authority as soon as a superior on the list becomes available, is able and assumes the role of the successor. An individual exercising the authority of a superior should keep a record of important actions taken and the period during which the authority is exercised.
| Department Functions and Recovery Time Objectives | Identifies essential department functions, and provides a time frame that each function must be restored after a business interruption or outage.
| Essential Function Worksheet(s) | Essential functions, those with a Recovery Time Objective of 12 hrs – 14 days, will have the highest priority for restoration, and may require employees with specific training or skills, or specialized work areas, tools, equipment or supplies. The Essential Function Worksheet(s) are used to provide greater detail to meet the demands to restore the Essential Functions.
| Emergency IT Access | If access to your department's information and systems is essential in an emergency, describe the department's emergency access plan below. This may include remote access (or authorization to allow remote access), contacting IT support, off-site data backup, backup files on flash drives, hard copies, IPhone/Android, use of alternate email systems (e.g., Yahoo, Gmail), or social media. Remember: technology may be limited or unavailable at the onset of a COOP emergency.
| Vital Records, Policies and Procedures | Identifies vital records and additional records or documents that the Department needs to carry out essential functions under emergency situations or are difficult to replace. Employees who normally perform certain key functions may not be available to continue their duties, so it is essential that documented policies and procedures be maintained by the Department. The policies and procedures should be available in multiple formats and cross-training should be provided within the work units.
| Internal and External Service Providers and Dependencies | Identifies certain dependencies upon services from both county/city departments and private service providers. A prepared list of providers will assist the department in a smooth transition during a COOP emergency.
| Operation Needs for Physical Relocation | Identifies the basic space, equipment and technology that would be required for each department to function in an alternate location during a COOP emergency. The information will be used to assist each department to resume operations at an alternate site.
| Mitigation Strategies | Identifies mitigation strategies that a department or unit may take to address each identified risk. Once a risk or hazard has been identified through planning, applying a mitigating action can prevent adverse outcomes or reduce their severity and impact.

## Plan Review & Revision
PLAN REVIEW AND REVISION
<<< Table of Contents |  |  |  | Health Department Information >>>
| Date | Reviewed/Revised By | Sections Reviewed/Revised | Description

## Dept. COOP Info
HEALTH DEPARTMENT INFORMATION
<<< Table of Contents |  |  |  | Leadership Succession >>>
I. Department Identification
Instructions: In this section, identify department leadership and personnel responsible for the development and implementation of department continuity of operations planning. Also identify any personnel responsible for the approval of this plan and its contents.
LHD Name
LHD Address 1
LHD Address 2
Main LHD Phone #
LHD Fax #
| Primary COOP Contacts | Name | Email | Office Phone | Mobile Phone
Health Officer
COOP Lead
COOP Alternate
II. Department Facilities
Instructions: List the buildings used by the department and its associated work units. Please include both primary and secondary uses (administrative, clinic, lab, etc.) and any special considerations or comments.
| Building | Primary Use | Secondary Use | Special Considerations/Comments
III. Department Overview
Instructions: Provide a brief description of the local health department. Include such items as principle services, number of staff, buildings, location, and space needs. The goal is to create a picture of the size of the local health department and the scope of its activities.
IV. Department COOP Objectives
Instructions: The goal of the LHD COOP plan is to assist the department to re-establish the essential services necessary to return to an operational state within 30 days after a major operational interruption. Briefly describe the range of services that you provide to others in the event of a long-term emergency. Do not include normal operations that can be suspended. It should be clear why your department must remain functional, at least in part, during a long-term emergency. Consider the priority tasks of the department. List them out and indicate whether they are performed daily, weekly, monthly, etc.
V. Unique Department Conditions
Instructions: Describe any unique situations or conditions that the department may face if it had to relocate for an extended period of time and or experience a 30% staffing loss.

## Lead Succession
LEADERSHIP SUCCESSION
<<< Table of Contents | [5 empty] | Delegation of Authority >>>
Succession to one office is essential in the event that Department Leadership is unavailable or incapable of performing their legal authorized duties, roles and responsibilities. Orders of succession provide for the orderly and predefined assumption of offices during day-to-day operations or during an emergency. Rights and Limitations of Succession: When the health officer is unavailable, the successors are authorized to make key policy and budgetary decisions for the department or work unit during day-to-day operations as well as COOP emergencies. The Head of Operations reserves the right to place limitations on the successor relating to Department /work unit expenditures. This delegation of authority will take effect when normal channels of direction are disrupted, and will terminate when normal channels are resumed.
I. Department Leadership Succession
| Role | Name | Title | Office Phone | Mobile Phone | Email | Other Means of Contact
Department Head
First Successor
Second Successor
Third Successor
Additional Contact
Additional Contact

## Del of Authority
DEPARTMENT DELEGATION OF AUTHORITY
<<< Table of Contents | [5 empty] | Department Functions >>>
Delegations of Authority specify who is authorized to make decisions or act on behalf of key institution or department of personnel. Delegation of Authority planning involves the following steps: - Identifying which authorities can, and should be, delegated; - Describing the circumstances under which the delegation would be exercised, including when it would become effective and when it would terminate; - Identifying limitations of the delegation; - Documenting to whom authority should be delegated; and - Ensuring designees are trained to perform their emergency duties. Delegations of Authority are required by statute in some cases. Certain incumbents in positions specified in the orders of succession are delegated authority to perform all duties and responsibilities of the leader. Authority to act as a successor should be exercised only with reasonable certainty that a superior is unable and unavailable to exercise authority and when immediate action is required. An individual acting as successor should be relieved of his or her authority as soon as a superior on the list becomes available, is able and assumes the role of the successor. An individual exercising the authority of a superior should keep a record of important actions taken and the period during which the authority is exercised. There are two types of authority that can be delegated: - Emergency Authority Ability to make decisions related to an emergency (i.e., COOP plan activation). Generally this type of authority lasts as long as the event exists. - Administrative Authority Ability to make decisions affecting operations beyond the duration of the event (e.g., hiring or fiscal operations).
I. Delegation of Authority
Instructions: Please document which authorities can and should be delegated, to whom, under what circumstances, including when delegation becomes effective and when it terminates, and by limitations. - List the authority to be delegated - Designate whether the authority is "emergency" or "administrative." - List the position which has this authority during normal agency operations. - List the position or positions that will receive the authority if it must be delegated. - List the conditions that would trigger a delegation of authority. - Outline procedures for the delegation, including notifying relevant staff of the transfer of power. - Indicate any limitations on the duration, extend, and scope of the delegation.
| Authority | Type of Authority | Position Holding Authority | Delegation to Position | Triggering Positions | Procedures | Limitations

## Department Functions
DEPARTMENT FUNCTIONS AND RECOVERY TIME OBJECTIVES
<<< Table of Contents |  |  |  | Essential Function >>>
Completing this table will help prioritize the recovery of primary functions and assist the local health department in determining essential functions that need to be restored immediately following an emergency. Essential functions are those functions that must continue with no or minimal disruption and enable us to provide vital services, maintain core business functions and protect the campus community, assets and infrastructure. Although all health department functions are important, not every function performed must be sustained during an emergency. Essential functions are broken into two priority levels: - Primary Essential Functions are those functions that would cause a catastrophic effect on the infrastructure or mission of the campus if an interruption occurred. Primary essential functions need to be restored as soon as possible with a recovery time objective of 12-24 hours. - Secondary Essential Function are those functions that can be interrupted for more than 24 hours but must be resumed within 14 calendar days (recovery time objective) of a disruption of normal business functions and continued until normal operations are resumed. A Recovery Time Objective is a period of time that the systems functions or applications must be restored after an outage.
I. Department Functions
Instructions: 1. List each basic function that the health department performs in the table below. Be concise - use 255 characters or less. If it is seasonal, provide the months. 2. For each of the primary functions listed in the table, recommend a Recovery Time Objective for restoring that function after an incident has occurred
| No. | Health Department Functions | Recovery Time Objective
|  |  | 24 hrs. | 14 days | 30 days
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40

## Essential Function
ESSENTIAL FUNCTION WORKSHEET
<<< Table of Contents |  |  | Emergency Access to Information and Systems >>>
I. Essential Function
Instructions: Complete one copy of this form for each essential function identified in the Health Department Functions worksheet that has a recovery time objective of 24 hours or 14 days. Make as many copies of this form as needed.
| Essential Function: (255 characters or less) |  |  |  | Recovery Time Objective
[5 empty] | 14 days | 30 days
Form completed by:
|  | Name | Title |  | Date
II. Essential Function Employees
Instructions: Identify the critical processes and services that are necessary to ensure the continuance of the function listed above. Identify key individuals and/or positions necessary to perform this function.
| Critical Process | Primary Employee Name and Position | Secondary Employee Name and Position |  | Special Comments
III. Specialized Physical Space Required to Meet this Essential Function
Instructions: Identify any specialized space(s) needed to perform this Essential Function. Do not include the spaces identified to meet the general operations needs of the department included on the Department General Operational Needs Worksheet.
| Intended Use of Space |  | Area Required, sq. ft. | Lighting | Heating/Cooling | Ventilation
III. Specialized Equipment Required to Meet this Essential Function
Instructions: Identify all specialized equipment required by this Essential Function, the utilities required, and resources for replacement if there is a catastrophic loss. Do not include equipment listed on the General Operational Needs worksheet.
| Quantity Required | Specialized Department Equipment | Utilities required by Equipment |  | Replacement Availability
|  |  | Indicate voltage required to operate equipment | Identify if water (W), natural gas (G) or ventilation (V) is required | If this equipment is available for loan or rental regionally, specify where

## Access to IT
EMERGENCY ACCESS TO INFORMATION AND SYSTEMS
<<< Table of Contents |  |  |  | Vital Records, Policies and Procedures >>>
I. Emergency Access to Information and Systems
Instructions: Describe the department's emergency access plan below. This may include remote access (or authorization to allow remote access), contacting IT support, off-site data backup, backup files on flash drives, hard copies, or use of alternate email systems (e.g., Yahoo, Gmail). Remember: technology may be limited or unavailable at the onset of a COOP emergency.
| No. | Information or System | Emergency Access Plan
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40

## Vital Records
VITAL RECORDS, POLICIES AND PROCEDURES
<<< Table of Contents | [5 empty] | Service Providers >>>
This worksheet is requesting information from the department regarding the vital records maintained or used by the work unit and the essential policies and procedures needed by the department to perform its essential functions. In COOP planning, vital records are those records or documents that the Department needs to carry out essential functions under emergency situations or are difficult to replace. Examples of vital records include blueprints, immunization records, financial records, personnel records, inventories, etc. Do not include records that may be useful but are not essential to providing a service. During a COOP emergency, employees who normally perform certain key functions may not be available to continue their duties. In order for a department to continue its essential functions, documentation in the form of policies and procedures are essential, and cross-training should be provided within the work units.
I. Department Vital Records
Instructions: Identify the vital records, databases or forms that are essential to the department operational needs during an emergency. Ensure such records are properly stored, backed up and safeguarded. Ensure all electronic records (programs and data files) are appropriately backed up and stored offsite.
| Record |  |  | Description/Name of Vital Record, Database or Form | Formats Available & Locations |  | Backup Method | Backup Frequency
| No. | LHD | County |  | Electronic Locations | Paper Locations
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
II. Department Essential Policies and Procedures
Instructions: Identify the department's critical policies and procedures. Ensure the policy and procedure documents are current and available in various formats; i.e., in paper form and online. Ensure appropriate individuals have access to copies of critical policy documents. Copies should be current and maintained at multiple locations.
| Record |  |  | Description/Name of Policy or Procedure | Formats Available & Locations |  | Positions Trained on Policy/Procedure
| No. | LHD | County |  | Electronic Locations | Paper Locations
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Service Providers
SERVICE PROVIDERS
<<< Table of Contents |  |  | Department General Operational Needs for Physical Relocation >>>
I. Internal Dependencies on County Departments
Instructions: Most health departments rely on Information Technology, Payroll/Purchasing/Finance, Public Safety and Facilities Services. List below the other products and services upon which the department depends and the internal departments or units that provide them.
| County Service or Product |  | County Provider | Point of Contact | Contact Phone
I. Dependencies on Outside Vendors/Service Providers
Instructions: List below the external products, services, suppliers and providers upon which the department depends. Identify the product or service, and the name and contact information for the primary provider and for alternate providers that can deliver the same products or services.
| Service/Product (255 characters or less) |  | Phone | Emergency 24/7 Phone | Alternate Contact Method
Primary Provider
Alternate Provider
Alternate Provider
Alternate Provider
| Service/Product (255 characters or less) |  | Phone | Emergency 24/7 Phone | Alternate Contact Method
Primary Provider
Alternate Provider
Alternate Provider
Alternate Provider
| Service/Product (255 characters or less) |  | Phone | Emergency 24/7 Phone | Alternate Contact Method
Primary Provider
Alternate Provider
Alternate Provider
Alternate Provider
| Service/Product (255 characters or less) |  | Phone | Emergency 24/7 Phone | Alternate Contact Method
Primary Provider
Alternate Provider
Alternate Provider
Alternate Provider
| Service/Product (255 characters or less) |  | Phone | Emergency 24/7 Phone | Alternate Contact Method
Primary Provider
Alternate Provider
Alternate Provider
Alternate Provider
| Service/Product (255 characters or less) |  | Phone | Emergency 24/7 Phone | Alternate Contact Method
Primary Provider
Alternate Provider
Alternate Provider
Alternate Provider
III. Key County Departments that Rely on Services
Instructions: List the Key Customers who rely on Local Health Department for services or information.
| Department(s) | Service(s) | Phone | Emergency 24/7 Phone | Alternate Contact Method
IV. Key External Organizations that Rely Upon LHD for Services
Instructions: List the Key Organizations who rely on the LHD for services or information. A pro-active approach in contacting important customers can be very effective in mitigating losses.
| Department(s) | Service(s) | Phone | Emergency 24/7 Phone | Alternate Contact Method

## Operational Needs
DEPARTMENT GENERAL OPERATIONAL NEEDS FOR PHYSICAL RELOCATION
<<< Table of Contents |  |  |  | Mitigation Strategies >>>
The information requested in this worksheet will be used to identify the basic space, technology and equipment that is necessary for the department to function in an alternate location during a COOP emergency, as defined by the COOP Planning scenario (below). Please review the instructions for each section below and answer the questions. The information provided will be used to assist the department in relocating should a COOP emergency occur. The alternate locations may include on-site or off-site locations. Remember that a relocation is a reaction to an emergency and critical needs must be met before department or personal preferences are met. When practical, some resources will be shared among multiple work units until full function is restored to normal. COOP Planning Scenario: For planning purposes, assume your department has experienced: - A severely damaged facility and will need to relocate to a different facility off site for 30 or more days, and - A 30% Staffing Loss. Departments or functions may be relocated as needed to conserve facilities or to isolate people from disease while continuation of critical functions.
I. Operational Need - Physical Space Requirements
Instructions for physical space needs: This section is requesting information about the spaces that would be needed by the department if it had to relocate to an alternate site during a COOP emergency. For each item listed below, indicate whether or not the type of space will be required with a 'Yes' or 'No'. The default answer is no. If the space is required, indicate a quantity (Qty) needed based on the number (#) of people or the number of "units" to plan for as defined within the line item.
| Required | Quantity/ Units | Description of spaces required by LHD | Quantity Planning Unit | Qualifiers/Notes | No
| No | 0 | Open Room, cap of 1-20 | # rooms | Open Rooms will have: desks or tables/chairs | Yes
| No | 0 | Open Room, cap of 11-35 | # rooms | Open Rooms will have: desks or tables/chairs
| No | 0 | Open Room, cap of 36-50 | # rooms | Open Rooms will have: desks or tables/chairs
| No | 0 | Open Room, cap of 51-80 | # rooms | Open Rooms will have: desks or tables/chairs
| No | 0 | Open Room, cap of 81-100 | # rooms | Open Rooms will have: desks or tables/chairs
| No | 0 | Office space with desk, chair | # people
| No | 0 | Conference space with table & chairs | # people
| No | 0 | Workspace, general | 10 sq ft/unit
| No | 0 | File cabinet storage | 1 cabinets/unit
| No | 0 | Secure storage | 10 sq ft/unit
| No | 0 | Private space for confidential discussion | # spaces
| No | 0 | Laboratory space, non-chemical usage | # spaces | Benches, electrical
| No | 0 | Laboratory space, chemical procedures | # rooms | Benches, electrical, room ventilation, sinks, water
| No | 0 | Laboratory space, specialized, please detail | # spaces | Detail here:
| No | 0 | Laboratory space, volatile chemicals | # spaces
| No | 0 | Studio space, specialized, please detail | # spaces | Detail here:
| No | 0 | Department storage | 200 sq ft/unit
| No | 0 | Retail space | 1000 sq ft/unit
| No | 0 | Kitchen space, food preparation | 200 sq ft/unit
| No |  | Access to a break area with refrigerator, sink, microwave, coffee pot | None | Break areas, if created, will be shared
| No | 0 | Secure storage for cash | None
Add Department specific request below
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
II. Operational Need - Equipment and Supplies
Instructions for critical equipment and supplies: This section is requesting information about the types of equipment, tools and supplies required by the department to conduct the essential functions following a relocation to an alternate site. For each item in the list below, indicate whether or not the item will be required with a 'Yes' or 'No'. If the item is required, indicate a quantity (Qty) needed based on the number of "units" to plan for as defined within the line item.
| Required | Quantity/ Units | Description of spaces required by LHD | Quantity Planning Unit | Qualifiers/Notes
| No | 0 | Work tables | 1 table/unit | Average size is 3 ft X 6 ft.
| No | 0 | Visitor chairs | 1 chair/unit
| No |  | Access to a photocopier | None | Photocopiers will be a shared resource
| No | 0 | Shelving, list | 8 linear ft/unit
| No | 0 | File cabinets | 1 ea/unit
| No | 0 | Vault or safe | 1 ea/unit
| No | 0 | Office supplies (pens, paper, clips, etc.) | # people
| No |  | Carts, 2-wheel | 1 ea/unit | Carts will be a shared resource
| No |  | Carts, 4-wheel | 1 ea/unit | Carts will be a shared resource
| No | 0 | Laboratory hoods or lab exhaust | 1 ea/unit
| No | 0 | Studio exhaust units, high temperature | 1 ea/unit
| No | 0 | Studio exhaust units, hazardous substances | 1 ea/unit
| No | 0 | Flammable Liquid Storage Cabinets, 45 gal capacity | 1 ea/unit
| No |  | Vehicle - car (shared) |  | Vehicles will be a shared resource
| No |  | Vehicle - pickup (shared) |  | Vehicles will be a shared resource
| No |  | Vehicle - truck (shared) |  | Vehicles will be a shared resource
Add Department specific request below
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
II. Operational Need - Technology and Communication
Instructions: This section is requesting information about the technology required by the department to conduct the essential functions following a relocation. For each item in the list below, indicate with 'Yes' or 'No' whether or not the item will be required. If the item is required, indicate a quantity (Qty) needed based on the number (#) of people or the number of "units" to plan for as defined within the line item.
| Required | Quantity/ Units | Description of spaces required by LHD | Quantity Planning Unit | Qualifiers/Notes
| No | 0 | A/V equipment | 1 ea/unit | Minimum: overhead projector and screen
| No | 0 | Television + VCR | 1 ea/unit
| No | 0 | Television + DVD | 1 ea/unit
| No | 0 | Email | # people
| No | 0 | Internet | # people
| No | 0 | Software: Microsoft Office Suite | # people
| No | 0 | Software: Define in Qualifiers/Notes | # people
| No | 0 | Software: Define in Qualifiers/Notes | 1 ea/unit
| No | 0 | Software: Define in Qualifiers/Notes | 1 ea/unit
| No | 0 | Software: Define in Qualifiers/Notes | 1 ea/unit
| No | 0 | Software: Define in Qualifiers/Notes | 1 ea/unit
| No | 0 | Software: Define in Qualifiers/Notes | 1 ea/unit
| No | 0 | Software: Define in Qualifiers/Notes | 1 ea/unit
| No | 0 | Software: Define in Qualifiers/Notes | 1 ea/unit
| No | 0 | Software: Define in Qualifiers/Notes | 1 ea/unit
| No | 0 | Software: Define in Qualifiers/Notes | 1 ea/unit
| No | 0 | Software: Define in Qualifiers/Notes | 1 ea/unit
| No | 0 | Software: Define in Qualifiers/Notes | 1 ea/unit
| No | 0 | Software: Define in Qualifiers/Notes | 1 ea/unit
| No | 0 | Software: Define in Qualifiers/Notes | 1 ea/unit
| No | 0 | Software: Define in Qualifiers/Notes | 1 ea/unit
| No | 0 | Software: Define in Qualifiers/Notes | 1 ea/unit
| No | 0 | Software: Define in Qualifiers/Notes | 1 ea/unit
| No | 0 | Software: Define in Qualifiers/Notes | 1 ea/unit
| No | 0 | Software: Define in Qualifiers/Notes | 1 ea/unit
| No | 0 | Software: Define in Qualifiers/Notes | 1 ea/unit
| No | 0 | Software: Define in Qualifiers/Notes | 1 ea/unit
| No | 0 | Drive mappings i.e. shared drive and any other drives | 1 ea/unit
| No | 0 | Hardware: Number of Desktop computers to be moved | 1 ea/unit
| No | 0 | Hardware: Number of Desktop computers to be borrowed | 1 ea/unit
| No | 0 | Hardware: Number of Laptop computers to be moved | 1 ea/unit
| No | 0 | Hardware: Number of Laptop computers to be borrowed | 1 ea/unit
| No | 0 | Hardware: Number of computer network outlets | 1 ea/unit
| No | 0 | Hardware: Number of printers to be moved | 1 ea/unit
| No | 0 | Hardware: Number of printers to be borrowed | 1 ea/unit
| No | 0 | Hardware: Number of scanners | 1 ea/unit
| No | 0 | Hardware: Wireless network access | 1 ea/unit
| No | 0 | Other peripheral, define | 1 ea/unit | Define:
| No | 0 | Network connection | 1 ea/unit
| No | 0 | Hardware: Number of Digital Telephone outlets | 1 ea/unit | Phone lines may be limited
| No | 0 | Hardware: Number of D-Term digital telephones | 1 ea/unit | Phone lines may be limited
| No | 0 | Hardware: Number of Analog Telephone outlets | 1 ea/unit | Phone lines may be limited
| No | 0 | Hardware: Number of Analog Telephones | 1 ea/unit | Phone lines may be limited
| No | 0 | Hardware: Number of fax lines | 1 ea/unit | Fax machines may be centrally located to serve multiple work areas
| No | 0 | List of Telephone Extensions to be transferred. Please detail | List each | List:
| No | 0 | Number of Cell Phones to be borrowed | 1 ea/unit
Add Department specific request below
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0
| No | 0

## Mitigation Strategies
MITIGATION STRATEGIES
<<< Table of Contents
I. Mitigation Strategies
Instructions: Review the information entered into this COOP Template and list the department's vulnerabilities that could be acted upon now to reduce the impact on operations. Then list the mitigation strategy that would be effective in reducing the risk to the department. For example, the department may wish to stock up on critical supplies or develop contingency work-at-home procedures. Be sure to set a time line to accomplish the mitigation action.
| Vulnerability | Mitigation Strategy | Mitigation Timeline |  | No
|  |  | Target Date | Completed | Yes